## Sheet1
C63 PROJECT STATUS REPORT - 04-10-28
¦¦++++++++++++++++ DUE DATE or CLOSING DATE++++++++++++¦¦
No. | Brief Title | Draft frm SC | Blt.Gp Inv. | C63 Blt - P/F | Recircul. | Public Rev. | ANSI appr | Editing | AVAILABLE | ACTION | RESPONSIBLE | COMMENTS | No.
C63.022 | [5 empty] | 06 Dec. 04 |  |  |  | Public Review for withdrawal |  |  | C63.022
C63.2 |  |  |  | P-22 June. 04 | [5 empty] | Ballot Resolution done 27 Oct .04 | Windler/Mertel |  | C63.2
C63.4 R2 |  | In process | [8 empty] | Berger |  | C63.4 R2
C63.5 | [5 empty] | 3 May. 04 | 24 June.04 | XX |  |  | IEEE Staff |  | C63.5
C63.7 | [5 empty] | 06 Dec. 04 |  |  |  | Sent to IEEE for pdf 29 June 04. | Secretary |  | C63.7
C63.8 |  | ?? | [8 empty] | Showers |  | C63.8
C63.12 |  | ?? | [8 empty] | Showers, plus Hofmann input |  | C63.12
C63.14 |  | In SC2 | [7 empty] | C63 will Review First Draft 04-10 | Southworth |  | C63.14
C63.15 |  |  |  |  | 12 Mar. 03 |  |  |  |  | Decide upon status | Secretary and Showers |  | C63.15
C63.16 |  |  |  | F-9 July. 04 | [5 empty] | Decide next step | Showers and Maas |  | C63.16
C63.17 | [12 empty] | C63.17
C63.18 |  | In SC 8 | [8 empty] | Silberberg |  | C63.18
C63.19R |  |  |  |  | 26 Nov. 04 | [5 empty] | Balloting Group |  | C63.19R
C63.22 | [6 empty] | 24 June.04 | XX |  |  | IEEE Staff |  | C63.22
C63.23 |  |  |  | F-1 May. 04 | [5 empty] | Blt FAILED - Resolve comments | Ed Bronaugh & Mike Windler |  | C63.23
C63.25 |  | Hold in SC5 | [7 empty] | Awaiting completion of C63.18 | Ed Hare |  | C63.25