## Sheet1
C63 PROJECT STATUS REPORT - 05-09
¦¦++++++++++++++++ DUE DATE or CLOSING DATE++++++++++++¦¦
No. | Brief Title | Draft frm SC | Blt.Gp Inv. | C63 Blt - P/F | Recircul. | Public Rev. | ANSI appr | Editing | AVAILABLE | ACTION | RESPONSIBLE | COMMENTS | No. | RLP REFERENCE
C63.022 |  | WITHDRAWN |  |  |  | 06 Dec. 04 |  |  |  | WITHDRAWN |  |  | C63.022
C63.2 | EM Noise & F'ld Str. Instr |  |  | P-22 June. 04 | REQUIRED |  |  |  |  | Need Recirc. Material | Windler - Have only Clean Draft 9 |  | C63.2 | DNH 05-02-01; RLP 05-02-08
C63.4 R2 |  | In SC1 | [8 empty] | Berger |  | C63.4 R2
C63.5 | Antenna Calibration |  |  |  |  | 3 May. 04 | 24 June.04 | XX | 20 Dec. 04 | None Required | N/A |  | C63.5
C63.6
C63.7 | OATS, Construction of |  |  |  |  | 06 Dec. 04 |  |  |  | Submit to ANSI | Secretary |  | C63.7
C63.8 | Compendium | CANCELLED | [7 empty] | PROJ. CANCELLED 04-10 MTG |  |  | C63.8
C63.9
C63.12 | EMC Limit Setting | [8 empty] | Act on responses to AI-0410-09 | C63 Steering Committee |  | C63.12
C63.13
C63.14 |  | In SC2 | [7 empty] | C63 will Review First Draft 05-10 | Southworth |  | C63.14
C63.15 | Immunity Meas. & Instr. |  |  |  | REQUIRED |  |  |  |  | Need Recirc. Material | Windler - Have only Clean Draft 7 |  | C63.15 | DNH 05-01-28; RLP 05-02-08
C63.16 | ESD Test Methodology |  |  | F-9 July. 04 | [5 empty] | New Draft in Preparation | Siberberg - ? |  | C63.16
C63.17 | Unlicensed PCS Devices |  | 8 Apr. 05 | [6 empty] | Draft AvaIlable for Ballot | Secretary |  | C63.17
C63.18 |  | In SC 8 | [8 empty] | Silberberg |  | C63.18
C63.19R | EMC Hearing Aids, et al |  |  |  | 25 Feb. 05 | 6 June. 05 |  |  |  | Conduct 4th Recirc Blt | Secretary |  | C63.19R
C63.22 | Guide for Aut'd. EMI Meas | [5 empty] | 24 June.04 | XX | 20 Dec. 04 | None Required | N/A |  | C63.22
C63.23 | Meas. Uncertainty |  |  | F-1 May. 04 | [5 empty] | New Draft in Preparation | Windler & Harrington |  | C63.23
C63.24 |  | Hold in SC5 | [7 empty] | Awaiting completion of C63.18 | Ed Hare |  | C63.25